## Sheet1
SBL Cost Study
Items | Details | # (Quantity) | Manhours | Costs | Per Hour Rate | Cost Details
Assumption | One SBL Set with 25 Screens
4 Characters
Some tasks run simultaneously
3 weeks to develop
PHASE 1
Conceptualization
Content Development | Conceptualization of stories and scenarios. | 1 | 16 | 400 | 25 | If client development this will be zero (0)
PHASE 2
Storyboarding
Documentation | Preparation of storyboard with character expressions. | 1 | 4 | 100 | 25
Storyboard Sketches | Rough sketches to complete the storyboard - guide to photo shoot and recording. | 25 | 8 | 80 | 10
Talents
Photo Character Sourcing | Compilation of talents for the photo shoot. | 4 | 16 | 400 | 25
VO Character Sourcing | Compilation of talents for the recording. | 4 | 16 | 400 | 25
Selection | Client selection of talents for photo shoot and recording. |  | 4 | 0 | 0 | Client time
Photo Talents Selected |  |  | 4 | 400 | 100 | Rate per talent (assumption 4 talents)
Voice Over Talents Selected |  |  | 4 | 400 | 100 | Rate per talent (assumption 4 talents)
PHASE 3
Photography
Preparation | Inventory of characters, roles, location, props, etc. | 1 | 4 | 60 | 15
Photo Session | Taking of photographs | 1 | 8 | 200 | 25 | Photographer Rate per hour
Photo Post Production | Editing of Photos | 25 | 8 | 200 | 25 | Post Production Rate per hour
Audio
Preparation | Inventory of characters, number of lines, expressions, tone, etc. | 1 | 4 | 60 | 15
SFX Sourcing | Inventory of SFX and sourcing |  | 4 | 60 | 15
Voice Over Recording | Recording of talents | 4 | 4 | 160 | 40 | Studio Rate per hour
Voice Over Post Production | Editing of Voice Overs | 25 | 8 | 200 | 25 | Studio Post Production Rate per hour
PHASE 4
Final Storyboard | Compilation of development storyboard for production references. | 1 | 4 | 100 | 25
Flash Development
Flash | Development of flash structure | 1 | 16 | 480 | 30
Photo Integration | Integration of Photos | 25 | 8 | 240 | 30
Audio Integration | Integration of Audio | 25 | 8 | 240 | 30
QC | Quality Check |  | 8 | 240 | 30
Final Revisions | Revisions |  | 16 | 480 | 30
Final Delivery | Delivery and integration of SBL to final location. |  | 2 | 50 | 25
Project Management | Misc. Management and coordination |  | 60 | 1800 | 30
TOTAL |  |  | 234 | 6750