## Sheet1
Compiled Schedule for 3 SBLs |  |  | Target Date: | June 2, 2006 (Friday)
Hourly Fishbone | 1
Pareto Executive | 2
5 Whys Executive | 3
Time | SBL | Location | Characters | Details | Screen Number | Props
7:30 - 8:30 |  | Ray on Location |  | Check Locations/ Orientation/ Arrange Staging Area for Preparatory Work
8:30 - 9:00 | 2 | Cafeteria | Employee 1,2,3 | Make-up/ Costumes/ Light Setup/ Props Setup |  | Coffee machine, Coffee cups, Crumpled Paper
9:00 - 9:30 | 2 | Cafeteria | Employee 1,2,3 | Photo Shoot | 1 | Coffee mugs
| 1 | Cafeteria | Bill and Nancy | Make-up/ Costumes/ Props Setup
9:30 - 10:30 | 1 | Cafeteria | Bill and Nancy | Photo Shoot | 1G, 2, 3, 4, 5 | Coffee machine, Coffee cups, Crumpled Paper
10:30 - 11:00 | 1 | Manufacturing Floor | Bob and Coordinator | Make-up/ Costumes/ Light Setup/ Props Setup |  | Machine & Cable core, Shutdown switch and clipboard, PC w/DMR screen
11:00 - 12:00 | 1 | Manufacturing Floor | Bob and Coordinator | Photo Shoot | 1A - B | Machine & Cable core, Shutdown switch and clipboard, PC w/DMR screen
| 1 | Cabler's workstation | Props | Photo Shoot | 1C - E | Stack of folders 2-3 Dynastar WO's on desk and OPM graphic
12:00 - 12:30 |  | Lunch Break
12:30 - 1:00 | 3 | Mel's office (Jane's office) | Gary and Jane | Make-up/ Costumes/ Light Setup/ Props Setup |  | 2 office chairs, table, office items, office area, Watch , Pen
EDM office (SVP's office)
In front of white wall in Rooms B & D
Hallway (or cubicle)
1:00 - 2:00 | 3 | All 5 Why's Shots | Gary and Jane | Photo Shoot | 1 to 6 | 2 office chairs, table, office items, office area, Watch , Pen
2:00 - 2:30 | 2 | Executive conf. Room or VCR | Larry, Tina, X, X | Make-up/ Costumes/ Light Setup/ Props Setup |  | Professional dress, Planners, Projector, Laptop, Memo, Paper, Coffee mugs, Pens, Piles of paper on desk, Powerpoint, Placecard "In Use" of room, Survey reports on table, Report
2:30 - 3:00 | 2 | Executive conf. Room or VCR | Larry, Tina, X, X | Photo Shoot | 1D - F,
3:00 - 3:30 | 2 | Executive conf. Room or VCR | Larry, Tina, X, X | Photo Shoot | 2G - E, 3 - 8 | Change of clothes for all 4 members
3:30 - 4:00 | 2 | Larry's Office | Larry | Costumes/ Light Setup/ Props Setup |  | Clock at 4:00, Pile of Surveys, FlipChart
4:00 - 4:30 | 2 | Larry's Office | Larry | Photo Shoot | 1B | Larry reading an e-mail (must see text), Larry without jacket on
[5 empty] | 8B | 3rd change of clothes for Larry
Clock at 4:00, Pile of Surveys, FlipChart
Team: * Assign someone to coordinate make-up and lights, location setup * Email to Ray a good time to call the photographer - contact number * Ideally (but not a must) the location should have big space for setup shots * Ray to prepare the binders that will be the sequence for storyboards (no need to worry about documentation) focus on schedule - guide on schedule - storyboards - list of characters - list of props